## Slide 1: iRequest Portal Dew Drops Status Update

## Slide 2: Dew Drops - iRequest Portal Status
Feature/Page/Epic | Grooming Status | Sprint | Dev Status | QC Status
iRequest Portal Header | Groomed | S1 | Ongoing, Proposed 16 March 2018 | Ongoing, Proposed 30 April 2018
iRequest Portal Home Page | Groomed | S1 | Ongoing, Proposed 16 March 2018 | Ongoing, Proposed 30 April 2018
My Requests Listing Page for Requester | Groomed | S1 | Ongoing, Proposed 16 March 2018 | Ongoing, Proposed 30 April 2018
Create Request for Requester | Groomed | S2 | Ongoing, Proposed 16 March 2018 | Ongoing, Proposed 30 April 2018
Edit Request for Requester | Groomed | S2 | Ongoing, Proposed 16 March 2018 | Ongoing, Proposed 30 April 2018
View Request Page for Requester | Groomed | S2 | Ongoing, Proposed 16 March 2018 | Ongoing, Proposed 30 April 2018
Approvals Listing Page for Requester | Groomed | S2 | Ongoing, Proposed 16 March 2018 | Ongoing, Proposed 30 April 2018
Configure Ad Banners for Admin | Groomed | S3 | Done | Not Started, Proposed 15 April 2018
Display Ad Banner on iRequest Home Page for Requester | Groomed | S3 | Ongoing, Proposed 16 March 2018 | Ongoing, Proposed 30 April 2018
FAQs Configuration for Admin | Groomed | S4 | Done | Not Started, Proposed 15 April 2018
Policy Configuration for Admin | Groomed | S4 | Done | Not Started, Proposed 15 April 2018
Contact Us Configuration for Admin | Groomed | S4 | Done | Not Started, Proposed 15 April 2018
FAQs on iRequest Portal | Groomed | S4 | Ongoing, Proposed 23 March 2018 | Ongoing, Proposed 30 April 2018
Policy on iRequest Portal | Groomed | S4 | Ongoing, Proposed 23 March 2018 | Ongoing, Proposed 30 April 2018
Procurement Team on iRequest Portal | Groomed | S4 | Ongoing, Proposed 23 March 2018 | Ongoing, Proposed 30 April 2018
Universal Search | Groomed | S4 | Ongoing, Proposed 23 March 2018 | Ongoing, Proposed 30 April 2018

## Slide 3: Thank You